NORDIC NARRATIVE REPORT – STATUS REPORT Dec. 31, 2011 – June 30, 2012.
Society “Association HIV.LV” (Biedriba Apvieniba HIV.LV”), Latvia
Project progress: 
The first installment  was received from SKA at 21 May, 2012.  Because of this fact organization covered expenses  in advance from other projects, and there were not many possibilities to do this.
Organization implemented such activities:

- Study Tour to Turku and Helsinki at 30 – 31 May, 2012

2 participants, involved into the project (Agita Seja and Aleksandrs Molokovskis)  visited all sites at cities mentioned above

- 1 one-day seminar on MAIDS issues, based on the second MAIDS module "Supporting People With Special Needs Living with HIV/AIDS" , held at Bauska (Zemgale region of Latvia) at 15 May, 2012: “Practical work with addicted and co-dependent persons”

Duration of the seminar 8 academic hours, and there were 27 participants at the seminar; from them working in specialties:

| Paramedics | 2 |
| --- | --- |
| Doctors | 1 |
| Social workers | 12 |
| Customers (social services), caregivers | 6 |
| Psychologists | 3 |
| Teachers | 1 |
| NGO 's representatives | 3 |
| HIV prevention makers | 2 |

Evaluation of the seminar and knowledge level was made. 27 evaluation forms were received from 27 participants. Evaluation results see bellow.

Seminar at Bauska, 15 May, 2012
                                          E V A L U A T I O N     S U M M A R Y
Evaluation of knowledge level (scale from 1 (very bad) to 10 (exellent))

| Chapter “Phenomenon of addiction” | Points (common and per participant) | Chapter “Intervention” | Points (common and per participant) |
| --- | --- | --- | --- |
| Before seminar | 193 : 27 = 7,15 | Before seminar | 163 : 27 = 6,04 |
| After seminar | 249 : 27 = 9,22 | After seminar | 243 : 27 = 9,00 |
| Increase the level of knowledge | 9,22 / 7,15 --> 29% | Increase the level of knowledge | 9,00 / 6,04 --> 49% |
| Chapter “Motivation of the addicted human” | Points (common and per participant) | Chapter “Counceling” | Points (common and per participant) |
| Before seminar | 171 : 27 = 6,33 | Before seminar | 216 :27 = 8,00 |
| After seminar | 232 : 27 = 8,59 | After seminar | 245 :27 = 9,07 |
| Increase the level of knowledge | 8,59 / 6,33 --> 36% | Increase the level of knowledge | 9,07 / 8,00 --> 13% |
| Chapter “Co-dependence” | Points (common and per participant) | Total (common points and per participant): Before seminar 934 : 5 : 27 = 6,92 After seminar 1216 : 5 : 27 = 9,00 Increase the level of knowledge 9,00 / 6,92 --> 30% |  |
| Before seminar | 191 :27 = 7,07 |  |  |
| After seminar | 247 :27 = 9,15 |  |  |
| Increase the level of knowledge | 9,15 / 7,07 = 29% |  |  |

Evaluation of organizational issues (scale from 1 (very bad) to 10 (exellent))

| Common level | 245 :27 = 9,07 points | Handouts, kits | 254 :27 = 9,41 points |
| --- | --- | --- | --- |
| Meals | 261 :27 = 9,67 points | Trainers work | 264 :27 = 9,78 points |
| Place and hall | 257 :27 = 9,52 points | Practical / interactive exercises | 256 :27 = 9,48 points |

Financial notes (if any explanation to your financial is needed, please provide it here):

No explanation or changes are needed this time.

Other

Because the project is started with delay, there is nothing to say in addition this time.

Project financial status

See the budget report in additional file attached.

Currency exchange rates used  in budget report are those:

http://ec.europa.eu/budget/inforeuro/index.cfm?Language=en

01/03/12        31/03/12	               LVL/EUR 	 1,431025 	 1 LVL is equal to 1,431025 EUR

01/04/12        30/04/12                LVL/EUR             1,427144            1 LVL is equal to 1,427144 EUR

01/05/12        31/05/12                LVL/EUR             1,429593            1 LVL is equal to 1,429593 EUR

01/06/12        30/06/12                LVL/EUR             1,432254            1 LVL is equal to 1,432254 EUR

Chairman of the Board,

Project leader                                                                                                               Aleksandrs Molokovskis

4 July, 2012

Program of the study visit to Helsinki and Turku, 30 - 31 May 2012, in English http://www.apvienibahiv.lv/docs/729/Projekti_2012/FinlandStudyTripENG.doc , in Russian http://www.apvienibahiv.lv/docs/729/Projekti_2012/Finland_StudyTripRUS.doc

2. MAIDS mācību modulis "Atbalsts cilvēkiem pie īpašām vajadzībām, dzīvojot ar HIV/AIDS" in Latvian http://www.apvienibahiv.lv/docs/729/projekti_2011/MAIDS_modulis_2_Lat_saitam.zip

Zemgales reģionālais seminārs „Praktiskais darbs ar atkarīgajām un līdzatkarīgajām personām", Bauskā, 2012. gada 15. maijs. Programma http://www.apvienibahiv.lv/docs/729/Projekti_2012/Progr_Bauska_15052012.doc

Some people combine the two works